## Backlog
Phase | Phase name | Feature | Category | Origin | Platform | Priority | Timeframe | Status | Notes / dependencies
0 | Infrastructure & Ownership Reset | Confirm GitHub/Vercel/Neon account ownership for all 3 repos | Infra | Session discussion — Aug 2026 | all | Must | Immediate | Done | Confirmed: back/designer/services repos are under the Altinsk GitHub account, owned by Omar. Still worth double-checking Vercel + Neon project ownership/billing directly in their own consoles.
0 | Infrastructure & Ownership Reset | Decide: consolidate repos into a GitHub Organization vs. keep as-is | Infra | Session discussion — Aug 2026 | all | Should | Immediate | Postponed | Only worth doing for cleaner team/collaborator access management going forward — ownership risk itself is already resolved. Decided 2026-08-23: not needed right now. No other developers are working on this application at the moment, so there's no collaborator-access-management need driving it -- the entire benefit an Organization would add. Revisit if/when a freelancer or team member joins. Real migration cost if done: every Vercel project's git integration would need manually reconnecting after any repo transfer.
0 | Infrastructure & Ownership Reset | Transfer or mirror the 3 repos to their final home | Infra | Session discussion — Aug 2026 | all | Should | Immediate | Not started | Depends on decision above. GitHub 'Transfer ownership' preserves history + auto-redirects; manual mirror (git push --mirror) only needed for a brand-new repo identity.
0 | Infrastructure & Ownership Reset | Re-link Vercel projects to repos' new location (if transferred) | Infra | Session discussion — Aug 2026 | web | Must | Immediate | Not started | Vercel's git integration is tied to the specific repo location — must be reconnected after any transfer or pushes stop auto-deploying.
0 | Infrastructure & Ownership Reset | Push pending local-only planning docs (CLAUDE.md, docs/roadmap.md, docs/status.md, docs/roadmap_backlog.xlsx) in all 3 repos | Housekeeping | Session discussion — Aug 2026 | all | Must | Immediate | Done | Currently sitting uncommitted locally in back/designer/services as of this session. Nothing else across the 3 repos is uncommitted or unpushed — verified via git status before this update. Update 2026-08-23: relocated into swales-backend/docs/ (SwalesApp-dev is now the only in-scope folder, per Omar's explicit instruction) and committed/pushed from there.
0 | Infrastructure & Ownership Reset | .env / secrets hygiene pass (document required vars via .env.example, confirm nothing secret is committed, separate values per environment) | Infra | Session discussion — Aug 2026 | backend | Must | Immediate | Done | Prompted by finding the local Postgres port mismatch (app config assumes 5432, actual local Postgres is 5433) and DATABASE_URL silently overriding local dev intent. Done 2026-08-23. Added .env.example to all 3 repos (backend/designer/services), documenting every process.env.* var actually referenced in code. Found and flagged (not removed): backend's DB_HOST/DB_NAME/DB_USER/DB_PASS + config/database.js are dead code (DATABASE_URL always wins); EMAIL_USER/EMAIL_PASS/Password_Reset_Url/Email_verify_Url/AllowedOrigins are unused leftovers. designer + services were both missing NEXT_PUBLIC_STRIPE_LINK_3/_5/_10 locally (only _CUSTOM set). services was also missing WEATHER_API_KEY2, NEXT_PUBLIC_SUPPORT_LINK, and 4 CARTO_WRI_MAP_TILE_URL vars. Confirmed no .env/.env.local currently tracked in any repo. Historical finding: services had a real .env.local committed to git history on 2025-04-23 (c6ae545) -- every secret in it has since been rotated, no live exposure, left history as-is. See status.md for full detail. Follow-up (2026-08-23): weather/map gaps confirmed resolved -- WEATHER_API_KEY2 (deliberate second OWM key, isolated rate-limit budget for the box-weather endpoint) and all 4 NEXT_PUBLIC_CARTO_WRI_MAP_TILE_URL1-4 (CARTO/WRI water-stress layer) now set in swales-services/.env.local. Support Link + Stripe donation links (NEXT_PUBLIC_SUPPORT_LINK, NEXT_PUBLIC_STRIPE_LINK_3/_5/_10/_CUSTOM across designer+services) remain ON HOLD until Omar opens a real business bank account -- code on both sides already reads identical env-var names, just needs real values once available.
0 | Infrastructure & Ownership Reset | Replace sequelize.sync({alter:true}) with real, reviewable migrations | Backend | Session discussion — Aug 2026 | backend | Must | Immediate | Done | back/server.js:48 and :133 auto-alter the live DB schema on every server start/deploy with no review step — the concrete mechanism behind 'a merge could break the running database.' Done 2026-08-23. This actually shipped in swales-backend (SwalesApp-dev), confirmed this session as the real production repo, not back -- see the doc-accuracy flag in status.md. Removed the unauthenticated public GET /api/db-sync endpoint (triggered sync({alter:true}) on demand) and the alter-on-local-start call; local startup now just calls sequelize.authenticate(). Added sequelize-cli config and 4 baseline migrations (Users/Elements/Projects/Shares) reproducing the existing schema exactly, verified column-for-column against production via information_schema. Both the Neon dev branch and production already had these tables, so baselined both by inserting the migration names into a new SequelizeMeta table -- no schema/data touched, confirmed via db:migrate:status showing all 4 as up. Shipped on chore/replace-sync-alter-with-migrations, merged to main, verified live: GET /api/db-sync now 404s in production. Side finding not yet acted on: repeated sync({alter:true}) calls likely left duplicate redundant unique constraints on Users.Email in production. Users.Email dedupe -- Done (2026-08-23): added a migration that dynamically drops every duplicate UNIQUE constraint on Users.Email, keeping one. Dev branch had 2 duplicates, production had 4. Tested on dev branch (2->1), shipped on chore/dedupe-users-email-constraint, PR'd (#5), merged to main (0bf6d6d). Applied to production directly by Omar (sequelize-cli --env production commands are hard-blocked for this assistant); verified live: production now shows a single Users_Email_key constraint.
0 | Infrastructure & Ownership Reset | Adopt Neon DB branching + Vercel Preview Deployments as the standard pre-merge testing workflow | Infra | Session discussion — Aug 2026 | all | Should | Immediate | Done | Gives an isolated database + isolated deployment per branch/PR with zero risk to production, without needing separate repos or projects. Partially done 2026-08-23. Vercel Preview Deployments already worked. Vercel's own Neon 'Connect a Project' dialog got permanently stuck with 'This project is already connected to the target store in one of the chosen environments', surviving deleting the DATABASE_URL vars, a hard reload, and reinstalling the integration -- unresolved, likely needs Vercel Support. Worked around it via Neon's GitHub integration instead: added .github/workflows/neon_workflow.yml giving every PR an isolated Neon branch forked from main, running npm run migrate against it as a pre-merge check, deleting the branch on PR close. Caught and fixed a wrong output name in Neon's own template (db_url_with_pooler doesn't exist; real one is db_url_pooled). Verified working end-to-end on PR #3, merged to main as be916dc. Still missing: wiring the branch into the live Vercel Preview deployment's DATABASE_URL for that PR (needs a VERCEL_TOKEN secret + a step calling Vercel's env API) -- pending a decision from Omar. See status.md. Fully done 2026-08-23: closed the remaining gap by wiring Neon branches into live Vercel Preview deployments too, via a workflow step calling Vercel's env API (VERCEL_TOKEN secret + VERCEL_PROJECT_ID/VERCEL_TEAM_ID variables), scoped to each PR's git branch. Added branch protection to main (blocks force-push/deletion, requires the Neon migration job to pass). Self-caught and fixed a security bug same session: a botched jq redaction leaked Vercel's encrypted DATABASE_URL envelope into this public repo's Actions log for one run; fixed the redaction and deleted that run's logs. Shipped on chore/wire-vercel-preview-db, merged as 5a3067d. See status.md for full detail.
0 | Infrastructure & Ownership Reset | Fix Google Sign-In: verify real Google id_token server-side (Option 1) | Backend / Security | Session discussion — Aug 2026 | backend | Must | Immediate | Done | back/controllers/socialAuthController.js currently trusts a client-supplied email + unverified token with no check at all — live account-takeover hole. Decided: verify Google's real id_token with google-auth-library, over patching the HMAC or adopting a full external auth provider. Done 2026-08-23. back/controllers/socialAuthController.js now verifies authToken via google-auth-library's OAuth2Client.verifyIdToken (signature, audience=GOOGLE_CLIENT_ID, issuer, expiry); email/firstName now come from the verified payload, not the request body. designer's NextAuth callback fixed to send Google's real account.id_token instead of a fabricated HMAC(secret, email) (services already did this). Shipped on fix/google-id-token-verification branches in back and designer, PR'd, merged to main, GOOGLE_CLIENT_ID added to back's Vercel production env. Verified live against https://swales-backend.vercel.app: missing/forged authToken correctly returns 400/401.
0 | Infrastructure & Ownership Reset | Create and maintain back/docs/status.md as the session-continuity doc | Housekeeping | Session discussion — Aug 2026 | all | Should | Immediate | Done | Created this session, imported via back/CLAUDE.md alongside roadmap.md. Updated at the end of significant sessions going forward.
A | Finish & Connect the Core | Design canvas (zones, beds, orchards, water features) | Canvas | List A – Phase 1 | web | Must | Weeks 1-4 | Not started | Built. Now being wired up with the plant DB + icon set delivered earlier.
A | Finish & Connect the Core | Plant & element database (region-aware, tagged) | Core data | List A – #1 / Phase 1 | backend | Must | Weeks 1-4 | Blocked | STATUS UPDATE 2026-08-30: schema, 171-species seed, companion-planting data, subcategory cleanup, and the derived layer field are all Done and applied to both the Neon dev branch and production. What remains - full icon population and the actual canvas merge (wiring /api/elements into the designer palette instead of static presets.json) - has NOT started and is blocked, waiting on Omar to source/create a real image per icon_key (the plant DB has zero images today). See future-concerns.md item 11.
A | Finish & Connect the Core | PDF export / clean map export | Workflow | List A – Phase 1 | web | Must | Weeks 1-4 | Not started | Already done — out of scope, no further work needed.
A | Finish & Connect the Core | Decide & implement a real auth token flow (replace HMAC workaround) | Technical debt | Codebase audit — Section A | backend | Must | Weeks 1-4 | Done | Done 2026-08-24. The HMAC(secret, email) workaround was already retired by the 2026-08-23 Google id_token fix; backend now mints a JWT (native or verified-Google login) used as a Bearer token. Decided: keep this single JWT/Bearer mechanism as shared auth for web + mobile, no refresh-token scheme for now. Extended JWT/cookie expiry 7d -> 30d for mobile-friendliness. See roadmap.md Phase A table and status.md for full detail.
A | Finish & Connect the Core | Backend: properly verify Google id_token (signature, audience, expiry) | Technical debt | Codebase audit — Section A | backend | Must | Weeks 1-4 | Done | The app now sends the real Google id_token, but /api/auth/google-signin still needs to verify it rather than accept any string. Flag to whoever owns that backend service. Done 2026-08-23. back/controllers/socialAuthController.js now verifies authToken via google-auth-library's OAuth2Client.verifyIdToken (signature, audience=GOOGLE_CLIENT_ID, issuer, expiry); email/firstName now come from the verified payload, not the request body. designer's NextAuth callback fixed to send Google's real account.id_token instead of a fabricated HMAC(secret, email) (services already did this). Shipped on fix/google-id-token-verification branches in back and designer, PR'd, merged to main, GOOGLE_CLIENT_ID added to back's Vercel production env. Verified live against https://swales-backend.vercel.app: missing/forged authToken correctly returns 400/401.
A | Finish & Connect the Core | Build a real AuthContext for the web app | Technical debt | Codebase audit — Section A | web | Must | Weeks 1-4 | Done | Done 2026-08-24. swales-designer already had context/AuthContext.tsx; the gap was specifically swales-services. Built swales-services/src/context/AuthContext.jsx matching services' existing conventions (accessToken localStorage key, NEXT_PUBLIC_API_BASE_URL + /api), wired into providers.js and login/page.js. Caught and fixed a real SSR regression before shipping (a copied {!isLoading && children} render gate was blanking Header/nav out of every static page - wrong for this SEO-dependent site). Verified end-to-end against the live rebuild backend via an invalid-token 401 -> self-clearing logout() path. Header.jsx (the live header) keeps its own separate auth logic - not migrated, out of scope. See status.md for full detail.
A | Finish & Connect the Core | Decide monetization framework (Free / free-for-contact / Core paid / Post-core) | Business model | Codebase audit — Section D | both | Must | Weeks 1-4 | Done | Decided 2026-08-24: Priestley 4-product ladder. Free = all maps + canvas, no gate. Free-for-contact = report/design download requires account - already built and working (ReportAuthGateModal). Core paid (monthly+yearly, price TBD) = enhanced report (multi-location comparison, unlimited regen, no upsell footer) at launch - NOT saved-limits/collaboration/AI-advisor/consulting-energy, those are deferred. Post-core undefined until real usage data. Blocked on Stripe/bank account. See status.md.
A | Finish & Connect the Core | Pinpoint global data extraction to user (auto site data from location pin) | Real-world data | List A – #0 | backend | Must | Weeks 1-4 | Not started | Infrastructure multiplier — do this early, it speeds up every later feature that needs site context.
A | Finish & Connect the Core | Shared account/data backend linking web + mobile | Infrastructure | New (mobile ask) | backend | Must | Weeks 1-4 | Not started | Folded into Phase B, not standalone (decided with Omar, 2026-08-24). swales-backend already IS the single shared backend serving both swales-designer/swales-services - one Users table, one Projects table, same auth. What's actually missing (photo-upload-with-GPS endpoint, mobile data model) is genuine Phase B scope, not a separate prerequisite.
A | Finish & Connect the Core | Decide the mobile app tech stack (React Native + Expo proposed) | Product decision | New (mobile ask) | mobile | Must | Weeks 1-4 | Done | Confirmed by Omar 2026-08-24: React Native + Expo (managed, TypeScript); offline-first local store (WatermelonDB/SQLite) with a sync queue; auth reused from shared_backend (auth-token decision now Done, see row 15); external vision API for photo/plant ID at MVP; Expo push for notifications. Full reasoning in roadmap.md's "First 2 weeks" item 5 and status.md.
A | Finish & Connect the Core | Add optional 2FA (TOTP) for user accounts | Security | Added 2026-08-24 (Omar) | backend + web | Should | Weeks 1-4 | Not started | Not urgent pre-monetization - account takeover today just exposes garden designs. Target: built and available before monetization goes live, not necessarily before the monetization framework itself is decided. TOTP (e.g. otplib), not SMS. See docs/future-concerns.md.
A | Finish & Connect the Core | Block disposable/temporary email domains at registration | Security | Added 2026-08-24 (Omar) | backend | Should | Weeks 1-4 | Not started | Anti-abuse: check the email domain against a maintained blocklist (e.g. disposable-email-domains) in register(), reject with a clear message. Pairs with the rate limiting already added 2026-08-24. See docs/future-concerns.md.
A | Finish & Connect the Core | Decide whether wind turbine sizing should use real wind speed | Product decision | Codebase audit — Section A | web | Should | Weeks 1-4 | Not started | Currently matches your own wind.txt spec verbatim, including an unused meanWindSpeed parameter — deliberately not changed until you confirm intent. A product decision, not a bug.
A | Finish & Connect the Core | Reconcile plant/element schema with the long-term relationships knowledge-graph vision | Core data | Codebase audit — Section C | backend | Should | Weeks 1-4 | Not started | The delivered 22-field flat schema (good_companions/avoid_near as strings) is a deliberate MVP. Your long-term vision is a ~50-field plant schema plus dozens of linked entity types (guilds, pests, diseases, cover crops...) tied together by a real relationships graph. Not a conflict — but worth a short pass now so early seed data doesn't need re-keying once the graph structure gets built, since that's explicitly a 2-3 year vision per your own notes, not this sprint.
A2 | Analysis Engine Quick Wins (parallel) | Site comparison (two locations side-by-side: wind/solar/soil) | Analysis cards | Codebase audit — Section B | web | Must | Weeks 1-10, parallel to A/B | Not started | Split-panel layout; data's already fetched - a fast win. Code-checked 2026-08-28: confirmed not built - no comparison UI/route exists yet in swales-services.
A2 | Analysis Engine Quick Wins (parallel) | Shareable link (encode lat/lng + active layer in the URL) | Analysis cards | Codebase audit — Section B | web | Must | Weeks 1-10, parallel to A/B | Done | One-line param change - near-zero cost, ship immediately. STATUS UPDATE 2026-08-30: built and verified live - MapComponent.jsx's updateLocationAndTimeGeoInfo now mirrors the pin into ?lat=&lng= via window.history.replaceState (the active layer was already encoded by the path itself), read back on mount via getUrlLocation() taking priority over stored location/geolocation. Added a Copy shareable link button (Share2 icon) next to the PDF-report button.
A2 | Analysis Engine Quick Wins (parallel) | PDF site report (wind + solar + soil analysis export) | Analysis cards | Codebase audit — Section B | web | Must | Weeks 1-10, parallel to A/B | Done | Distinct from the design-canvas PDF export in Phase A - this is the energy/soil analysis report. STATUS UPDATE 2026-08-28: built - utils/combinedReportPdf.js's generateCombinedReport already produces this (and more: water stress, flood risk, precipitation, elevation, sun position, contour), wired through the shared site-data cache (see status.md's 2026-08-27 entry). What's still open is the monetization gate, not the report itself - ReportAuthGateModal currently only checks login, not payment.
A2 | Analysis Engine Quick Wins (parallel) | Combined renewable score (single energy-potential badge: wind + solar) | Analysis cards | Codebase audit — Section B | web | Should | Weeks 1-10, parallel to A/B | Not started | Code-checked 2026-08-28: confirmed not built - solar and wind scores/badges exist independently (SolarCard.jsx, WindDashboard.jsx) but no single combined wind+solar badge found.
A2 | Analysis Engine Quick Wins (parallel) | ROI/payback calculator (electricity bill + budget -> payback years) | Analysis cards | Codebase audit — Section B | web | Should | Weeks 1-10, parallel to A/B | Done | Uses existing wind/solar data - pairs naturally with bankability in the W track. Code-checked 2026-08-28: confirmed not built as a real calculator - SolarCard.jsx currently only has tooltip text manually explaining the payback math, no interactive calculator. Shipped 2026-09-13 as the Solar & Wind ROI/Payback Calculator under Field Calculators (/field-calculators/solar-wind-payback-calculator) - real interactive calculator now exists, standalone rather than added to SolarCard.jsx.
A2 | Analysis Engine Quick Wins (parallel) | Optimal install month recommender (seasonal solar + wind data) | Analysis cards | Codebase audit — Section B | web | Should | Weeks 1-10, parallel to A/B | Not started | Built on SmartSolarAdvisor's existing seasonal data. Code-checked 2026-08-28: the foundation is real (smartSolarAdvisor.js already computes bestMonth/worstMonth PV output) but it's framed around peak generation, not an install-timing recommendation, and doesn't factor wind data - still not started as its own feature.
A2 | Analysis Engine Quick Wins (parallel) | Onboarding tooltip tour (4-step walkthrough) | Onboarding | Codebase audit — Section B | web | Should | Weeks 1-10, parallel to A/B | Not started | Distinct from the broader 'onboarding' beginner-mode item in Phase D - this is a lightweight tour for the existing analysis-card UI, shippable now. Code-checked 2026-08-28: confirmed not built - no tour/walkthrough component found.
A2 | Analysis Engine Quick Wins (parallel) | Precipitation card — Option A (static: intensity badge, rainfall chart, guidance, soil-saturation estimate) | Analysis cards | Codebase audit — Section B | web | Should | Weeks 1-10, parallel to A/B | Done | Ship this static version first (matches the SolarCard/WindDashboard pattern), per your own recommendation. STATUS UPDATE 2026-08-28: built - components/ui/PrecipitationCard.jsx exists, fully implemented (intensity badge, rain animation, guidance), wired into LayerDataPanel.jsx.
A2 | Analysis Engine Quick Wins (parallel) | Composite soil health score (0-100, weighted, with trend indicator) | Analysis cards | Codebase audit — Section B | web | Should | Weeks 1-10, parallel to A/B | Done | STATUS UPDATE 2026-08-28: built - components/ui/SoilCard.jsx's computeScore() already implements a 0-100 weighted soil health score with tiered guidance (Good/Fair/Poor).
A2 | Analysis Engine Quick Wins (parallel) | Crop suitability engine (ranks wheat/maize/legumes/vegetables/fruit trees with reasons) | Analysis cards | Codebase audit — Section B | web | Should | Weeks 1-10, parallel to A/B | Not started | Code-checked 2026-08-28: confirmed not built - no crop-suitability ranking logic found.
A2 | Analysis Engine Quick Wins (parallel) | Amendment calculator (exact kg/hectare dosing) | Calculators | Codebase audit — Section B | web | Should | Weeks 1-10, parallel to A/B | Done | Code-checked 2026-08-28: confirmed not built as a real calculator - SoilCard.jsx only has generic 'targeted amendment' guidance text, no kg/hectare dosing calculation. Shipped 2026-09-13 as the Soil Amendment Rate Calculator under Field Calculators (/field-calculators/amendment-rate-calculator) - real interactive calculator now exists, standalone rather than added to SoilCard.jsx.
A2 | Analysis Engine Quick Wins (parallel) | Cross-layer integration (soil x precipitation x sun x wind unified farm advisory) | AI assist | Codebase audit — Section B | web | Should | Weeks 1-10, parallel to A/B | Not started | Overlaps ai_advisor/decision_layer conceptually — likely the same underlying advisory engine applied to the analysis cards instead of the design canvas. Worth deciding if these converge into one engine.
A2 | Analysis Engine Quick Wins (parallel) | UI consistency pass (spacing, tooltips, blog-post links, subtle animation across cards) | Onboarding | Codebase audit — Section B | web | Should | Weeks 1-10, parallel to A/B | Not started
A2 | Analysis Engine Quick Wins (parallel) | "Find best spot nearby" (draw a radius, rank top 3 solar/wind locations) | Analysis cards | Codebase audit — Section B | web | Could | Weeks 1-10, parallel to A/B | Not started
A2 | Analysis Engine Quick Wins (parallel) | Shadow/obstruction input (mark trees/buildings to adjust solar estimate) | Analysis cards | Codebase audit — Section B | web | Could | Weeks 1-10, parallel to A/B | Not started
A2 | Analysis Engine Quick Wins (parallel) | Saved pins with notes (localStorage OK for v1) | Analysis cards | Codebase audit — Section B | web | Could | Weeks 1-10, parallel to A/B | Not started | Code-checked 2026-08-28: confirmed not built - no saved-pins/localStorage-notes feature found.
A2 | Analysis Engine Quick Wins (parallel) | RainAdvisor service — Option B (irrigation decisions, flood/runoff risk, swale/water-harvesting sizing) | AI assist | Codebase audit — Section B | web | Could | Weeks 1-10, parallel to A/B | Not started | Layer in after precipitation_card ships, the same way SmartSolarAdvisor was bolted onto the sun tracker — don't build both at once.
A2 | Analysis Engine Quick Wins (parallel) | Soil depth profile visualization (SoilGrids 0-100cm) | Analysis cards | Codebase audit — Section B | web | Could | Weeks 1-10, parallel to A/B | Not started
A2 | Analysis Engine Quick Wins (parallel) | Carbon sequestration estimate (tonnes/hectare/year, linked to carbon credit schemes) | Analysis cards | Codebase audit — Section B | web | Could | Weeks 1-10, parallel to A/B | Not started
A2 | Analysis Engine Quick Wins (parallel) | Erosion risk score (texture + bulk density + slope + rainfall intensity) | Analysis cards | Codebase audit — Section B | web | Could | Weeks 1-10, parallel to A/B | Not started
B | Mobile MVP — Capture & Identify | Photo recognition AI (trees, plants, flowers, mushrooms) | AI assist | List B | mobile | Must | Weeks 5-12 | Not started | Merge with 'Natural identifier' below — same feature. This is the single best reason to install the mobile app.
B | Mobile MVP — Capture & Identify | Natural identifier | AI assist | List B | mobile | Must | Weeks 5-12 | Not started | Duplicate of photo_recognition — ship as one feature, not two.
B | Mobile MVP — Capture & Identify | Location-based site/observation logging (GPS pins) | Real-world data | New (mobile ask) | mobile | Must | Weeks 5-12 | Not started | Foundation for biodiversity tool, mushroom map, and community map — build the pin system once, reuse everywhere.
B | Mobile MVP — Capture & Identify | "My Sites/Designs" synced view from web account | Infrastructure | New (mobile ask) | mobile | Must | Weeks 5-12 | Not started | Read-only on mobile at first — don't try to rebuild the design canvas on a phone screen. Confirmed there's no existing native app to build on — this is a genuine fresh build.
B | Mobile MVP — Capture & Identify | Weather integration | Real-world data | List B | both | Should | Weeks 5-12 | Not started | Useful context for field capture; relatively cheap via a weather API.
C | Mobile Social Layer | Core social mechanics: comments, likes, sharing | Social | New (mobile ask) | mobile | Must | Weeks 13-19 | Not started | Build once as shared infrastructure — every social feature below (community, success stories, etc.) sits on top of this.
C | Mobile Social Layer | Community (feed of designs/observations) | Social | List B | mobile | Must | Weeks 13-19 | Not started
C | Mobile Social Layer | Community map + Quora-style Q&A | Social | List C | mobile | Should | Weeks 13-19 | Not started | Q&A layer can start simple — threaded comments on map pins.
C | Mobile Social Layer | Biodiversity observation tool | Real-world data | List B | mobile | Should | Weeks 13-19 | Not started | Reuses the location_logging pin system from Phase B.
C | Mobile Social Layer | Success Stories | Social | List B | mobile | Should | Weeks 13-19 | Not started
C | Mobile Social Layer | Decide the social/engagement layer's style (Twitter-like vs Instagram-like vs other) | Social | Codebase audit — Section F | mobile | Should | Weeks 13-19 | Not started | Open question from your own notes — decide before building out social_engine/community_feed in detail, since it shapes the UI pattern (feed vs. grid, text-first vs. photo-first).
C | Mobile Social Layer | Perma app map (gamified exploration, like Yusuf's map game) | Social | List C | mobile | Could | Weeks 13-19 | Not started | Builds on community_map — sequence after the base map has real content.
C | Mobile Social Layer | Mushroom map | Real-world data | List B | mobile | Could | Weeks 13-19 | Not started | A filtered view of the same pin system, not a separate build.
C | Mobile Social Layer | Messaging app (DMs) | Social | List B | mobile | Could | Weeks 13-19 | Not started | Real engineering + moderation surface — confirm it's worth it before/instead of just comments+DM-via-email.
D | Reference & Content Layer | Usability & onboarding (beginner mode) | Onboarding | List A – #8 | both | Must | Weeks 20-27 | Not started | Don't skip this — it's explicitly why MyPermagarden beats Swales today on ease of entry.
D | Reference & Content Layer | Wiki | Learning | List B | both | Should | Weeks 20-27 | Not started
D | Reference & Content Layer | Trees reference pages | Core data | List B | both | Should | Weeks 20-27 | Not started | Pulls from the same plant_database schema — content expansion, not new architecture.
D | Reference & Content Layer | Plants reference pages | Core data | List B | both | Should | Weeks 20-27 | Not started | Same as above.
D | Reference & Content Layer | Energy Calculators | Calculators | List B | both | Should | Weeks 20-27 | Done | Done 2026-09-13 - folded into the Field Calculators row (65) rather than built separately; see that row's notes. All 8 energy calculators (solar array, hydro power, battery bank, inverter, wind output, solar/wind payback, biogas potential, hybrid system balancer) live under /field-calculators.
D | Reference & Content Layer | Field Calculators | Calculators | List B | both | Should | Weeks 20-27 | Done | Done 2026-09-13 - all 26 calculators live across 6 categories (Earthworks & Permaculture, General Agriculture, Vertical Farming, Microgreens, Aquaculture & Aquaponics, Energy). Folded in Energy Calculators (row 64) plus 3 net-new categories not originally scoped here. Each calculator: real hand-verified formula/methodology, SEO/GEO article + FAQ schema, standalone manual-entry (no map/API dependency). Hub page at /field-calculators. See status.md's 2026-09-13 entries for full build/sourcing detail. swales-services commits 111ddcb..290d5cf.
D | Reference & Content Layer | Design library / public gallery | Social | List A – Phase 5 / List B – Design | both | Should | Weeks 20-27 | Not started | Needs real user designs to populate — sequence after Phase B/C produce some.
D | Reference & Content Layer | Templates (UK garden, homestead, agroforestry) | Onboarding | List A – Phase 5 | web | Should | Weeks 20-27 | Not started
D | Reference & Content Layer | Flowers reference pages | Core data | List B | both | Could | Weeks 20-27 | Not started | Same schema, lower priority content set.
D | Reference & Content Layer | Animals reference pages | Core data | List B | both | Could | Weeks 20-27 | Not started | Same schema, extends the animal_system category already in the seed data.
D | Reference & Content Layer | Mushrooms reference pages | Core data | List B | both | Could | Weeks 20-27 | Not started | Same schema.
D | Reference & Content Layer | Materials reference/catalog | Core data | List B | both | Could | Weeks 20-27 | Not started
D | Reference & Content Layer | Books and magazines library | Learning | List B | both | Could | Weeks 20-27 | Not started
D | Reference & Content Layer | Resources library | Learning | List B | both | Could | Weeks 20-27 | Not started | Overlaps books_magazines — consider one unified library section.
D | Reference & Content Layer | Ideas (inspiration gallery) | Learning | List B | both | Could | Weeks 20-27 | Not started | Overlaps design_gallery below — merge if possible.
D | Reference & Content Layer | "Permaculture" content hub / landing page | Learning | List B | both | Could | Weeks 20-27 | Not started
E | Education & Gamification | Yield planner | Time/succession | List B | both | Should | Weeks 28-34 | Not started
E | Education & Gamification | Planner / Tips / To-do list | Time/succession | List B | mobile | Should | Weeks 28-34 | Not started
E | Education & Gamification | Quiz / SwalesQuiz | Learning | List B / List C | both | Should | Weeks 28-34 | Not started | Merge Quiz + SwalesQuiz + 'Test your knowledge' into one feature.
E | Education & Gamification | Test your knowledge | Learning | List B | both | Should | Weeks 28-34 | Not started | Duplicate of quiz — don't build twice.
E | Education & Gamification | Events calendar | Social | List B | both | Could | Weeks 28-34 | Not started
E | Education & Gamification | Competitions / challenges / tests | Gamification | List B | both | Could | Weeks 28-34 | Not started | Needs an active user base to have anyone to compete against — correctly gated here, not earlier.
E | Education & Gamification | Coins / earnings or similar | Gamification | List B | both | Could | Weeks 28-34 | Not started | Merge with 'Rewards using the app' — same mechanic.
E | Education & Gamification | Rewards using the app | Gamification | List B | both | Could | Weeks 28-34 | Not started | Duplicate of coins_rewards.
F | Platform & Business Layer | 3D model / visualization | Canvas | List A – #12 | web | Later | Month 9+ | Not started | Most expensive line item relative to payoff. Recommend skipping until 2D + AI + data clearly beat AgroForest Designer on their own turf.
F | Platform & Business Layer | Swales marketplace | Marketplace/biz | List C | both | Later | Month 9+ | Not started | Needs finished designs worth trading — gate on Phase B/C/D producing real content.
F | Platform & Business Layer | Services directory (consultants/designers) | Marketplace/biz | List B | both | Later | Month 9+ | Not started
F | Platform & Business Layer | Quotes (supplier/contractor quote requests) | Marketplace/biz | List B | both | Later | Month 9+ | Not started | Pairs naturally with services + cost_estimation.
F | Platform & Business Layer | Hardware (physical products) | Marketplace/biz | List C | both | Later | Month 9+ | Not started | This is close to a separate business — treat as its own go/no-go decision, not a feature ticket.
F | Platform & Business Layer | School | Learning | List B | both | Later | Month 9+ | Not started | Merge with skool_mentors + mind_valley — pick one education-platform model, don't build three.
F | Platform & Business Layer | Skool of mentors idea | Learning | List B | both | Later | Month 9+ | Not started | Duplicate bucket — see school.
F | Platform & Business Layer | Mind Valley-style permaculture course platform | Learning | List B | both | Later | Month 9+ | Not started | Duplicate bucket — see school.
F | Platform & Business Layer | Swales Media (video/photo content hub) | Content | List B | both | Later | Month 9+ | Not started | Merge with journal_magazine — one content hub, not two.
F | Platform & Business Layer | Journal or news magazine | Content | List B | both | Later | Month 9+ | Not started | Duplicate bucket — see swales_media.
F | Platform & Business Layer | Permaculture Photo book | Content | List B | both | Later | Month 9+ | Not started
F | Platform & Business Layer | A KPI-led movement (impact metrics framework) | Marketplace/biz | List C | both | Later | Month 9+ | Not started | More a marketing/positioning initiative than a build item.
F | Platform & Business Layer | Integrations (GIS, farm tools) | Real-world data | List A – Phase 5 | backend | Later | Month 9+ | Not started
F | Platform & Business Layer | Technical considerations in the future (infra/scaling) | Infrastructure | List C | backend | Later | Month 9+ | Not started | Revisit once there's real load to scale for.
W | Web Pro Track (parallel) | AI design assistant ("Swales AI") — swale placement, orchard siting, windbreak recs | AI assist | List A – Phase 2 / List C – Swales AI / List B – Design with AI help | web | Must | Runs alongside B–E | Not started | Already in background dev. Treat Swales AI, Decision Intelligent Layer, and Design-with-AI-help as ONE product surface, not three.
W | Web Pro Track (parallel) | Guild builder (auto-suggest combos, conflict warnings) | AI assist | List A – Phase 2 | web | Must | Runs alongside B–E | Not started | Directly uses the good_companions/avoid_near fields already in the delivered schema.
W | Web Pro Track (parallel) | Reports (site analysis, water flow, design rationale) | Workflow | List A – Phase 3 / List C | web | Must | Runs alongside B–E | Not started | This is the monetization unlock — what consultants pay for.
W | Web Pro Track (parallel) | Decision intelligent layer | AI assist | List C | web | Should | Runs alongside B–E | Not started | Merge into ai_advisor — same underlying engine, don't build twice. Also overlaps cross_layer_advisory below — one engine, not three.
W | Web Pro Track (parallel) | Zones & sectors auto-generation (Zone 1-5, sun/wind/water) | Canvas | List A – Phase 2 | web | Should | Runs alongside B–E | Not started
W | Web Pro Track (parallel) | Cost + materials estimation | Workflow | List A – Phase 3 | web | Should | Runs alongside B–E | Not started
W | Web Pro Track (parallel) | Client sharing (view-only links, commenting) | Workflow | List A – Phase 3 | web | Should | Runs alongside B–E | Not started
W | Web Pro Track (parallel) | Bankability for systems (financial/ROI viability) | Workflow | List A – #13 | web | Should | Runs alongside B–E | Not started | Real differentiator — no competitor in the teardown has this. Worth protecting time for.
W | Web Pro Track (parallel) | Growth simulation (trees over 5-10 years) | Time/succession | List A – Phase 4 | web | Could | Runs alongside B–E | Not started | Slides to late W / early F if capacity is tight — real engineering effort.
W | Web Pro Track (parallel) | Water behavior modeling (before/after swales) | Time/succession | List A – Phase 4 | web | Could | Runs alongside B–E | Not started | Same caveat as growth_sim.
W | Web Pro Track (parallel) | Yield projections | Time/succession | List A – Phase 4 | web | Could | Runs alongside B–E | Not started
W | Web Pro Track (parallel) | Succession planning | Time/succession | List A – #5 / Phase 4 | web | Could | Runs alongside B–E | Not started
P | Parked / Needs Clarification | "Eco system Features" (as named in your Notion list) | Unclear | List C | — | — | — | Not started | Title alone doesn't tell me what's inside this page — looked private/inaccessible to me. Overlaps growth_sim/water_modeling/yield_projection unless it means something else — flag for you to clarify or fold in.

## Phase Summary
Phase | Name | Timeframe | Approx dates | Platform | # Items | Must | Should | Could | Later
0 | Infrastructure & Ownership Reset | Immediate | Before any repo migration — Aug 2026 | Infra/backend | 10 | 6 | 4 | 0 | 0
A | Finish & Connect the Core | Weeks 1-4 | ~mid-Aug – mid-Sep 2026 | Web + backend | 14 | 10 | 4 | 0 | 0
A2 | Analysis Engine Quick Wins (parallel) | Weeks 1-10, parallel to A/B | ~mid-Aug – late Oct 2026 | Web | 20 | 3 | 10 | 7 | 0
B | Mobile MVP — Capture & Identify | Weeks 5-12 | ~mid-Sep – mid-Nov 2026 | Mobile | 5 | 4 | 1 | 0 | 0
C | Mobile Social Layer | Weeks 13-19 | ~mid-Nov – early Jan 2027 | Mobile | 9 | 2 | 4 | 3 | 0
D | Reference & Content Layer | Weeks 20-27 | ~early Jan – late Feb 2027 | Both (mobile-first) | 16 | 1 | 7 | 8 | 0
E | Education & Gamification | Weeks 28-34 | ~late Feb – mid-Apr 2027 | Both | 8 | 0 | 4 | 4 | 0
F | Platform & Business Layer | Month 9+ | ~Apr 2027 onward, gated on usage data | Both | 14 | 0 | 0 | 0 | 14
W | Web Pro Track (parallel) | Runs alongside B–E | ~Sep 2026 – Apr 2027 | Web | 12 | 3 | 5 | 4 | 0
P | Parked / Needs Clarification | — | — | — | 1 | 0 | 0 | 0 | 0